## Sheet1
Issue Id | Raised | Description | Severity | Current Status | Disposition | Remediation steps | Customer review
CBC-01 |  | Disable video auto-play | Significant | Closed | Resolved
CBC-02 |  | Slideshow - content focus order | Moderate | Closed | Resolved
CBC-03 |  | Slideshow - dialog focus order | Moderate | Closed | Resolved
CBC-04 |  | Make video player accessible (replace vimeo with Able player) | Severe | Open | Investigating | In progress / testing
CBC-05 |  | page 22/27 - make content accessible (use semantic HTML) | Moderate | Closed | Resolved
CBC-06 |  | infographic - page 41 group page heading elements | Usability | Open | Resolved
CBC-07 |  | infographic - make flip cards accessible | Severe | Open | Planned | accessible html-based pages will be created
CBC-08 |  | infographic - Page 41 - hide braces | Usability | Open | Resolved
CBC-09 |  | infographic - page 50 make accessible | Moderate | Open | Planned | accessible html-based pages will be created
CBC-10 |  | Page 55 - make content accessible (fix headings) | Moderate | Open | Planned
CBC-11 |  | Enable form to gather accessibility feedback and ensure it is accessible | Severe | Open | Investigating | In progress
CBC-12 |  | Page 39 - after clicking on the begin button. focus should land on the video Play button (instead of the next page button) | Moderate | Open | Planned

## Lookups
Severity Level | Status | Disposition
Severe | Open | Planned
Significant | Closed | Deferred
Moderate | Investigating | Investigating
Usability |  | Resolved