## Sheet1
WASHINGTON STATE STUDENT SERVICES COMMISSION WORKPLAN: 2017-2018
System Direction Goal: Economic Demand ~ Strengthen state and local economies by meeting the demands for a well-educated and skilled workforce. Facilitated by Guided Pathways Committee
Objectives | Strategies | Intended Outcomes | Action/Updates
A. Idenitfy effective tools to assist CTCs develop appropriate onboarding, career identification and exploration, and advising practices that support principles of Guided Pathways framework. | A1. Convene small workgroups with appropriate Council representation to develop best practices to be delivered to WSSSC by May 2018. | A1. Provide recommendations for CTCs regarding: a. onboarding; b. career advising into and within pathways; c. creation of educational plans; d. advising policies and procedures to promote retention and completion; and e. job placement or transfer advising | Partnerd with SBCTC to host a tecnology conference in conjunction with Pathways work. Currently working to develop emerging practice and create a space on the SBCTC Stutent Success center to house this information.
B. Identify effective tools to assist CTCs in creating Degree Maps that support Guided Pathways Framework | B1. Survey CTCs to identify the variety, scope, and approaches to creating comprehensive, effective, and student-minded degree maps. B2. Collaborate with instruction/Instruction Commission to identify these approaches and to assure broad student services integration in the process. | B1 & B2. Provide recommendations for CTCs regarding best practices for creating student-centered: scheduling matrices; degree maps; program guides; and other tools that support guided pathways. B1 & B2. Provide recommendations for CTCs to create Guided Pathways that maximize the ability of students earning workforce ready credentials to transfer to bachelor programs. | Many of the emerging best practicices in these areas have been shared as part of the Pathways initiitive. Most of these are in early stages of adoption. As more information is developed it will be more widely shared and housed on the Student Success website at SBCTC
C. Develop funding and financial aid options that maximize student access and retention while minimizing student debt. | C1. Convene taskforce including representatives from Financial Aid, WorkForce Education and Grants, Basic Skills, and VA to develop best practices for braided funding models to be delivered to WSSSC and IC by May 2018 C2. Convene taskforce of ARC and FAC reps to develop recommendations that relate to student communication, coding, and compliance | C1. Provide recommendations for creating braided funding models for Guided Pathways that maximize federal, state, and institutional funding options that support students--including those without a high school credential to transition--to complete degree programs. C2. Provide recommendations for student coding within Guided Pathways that allow students to make a more informed degree decision in 2nd or 3rd quarter of study | Conversations have commenced, but more specificity will be needed and formally coordinated with relevant councils. Wtih regard to C2, thus far, "taskforces" have been developed on an ad hoc basis; we anticipate more formality and consistency as we approach broader implementation.
D. Build collaborative opportunities to full take advantage of overlapping areas within the pathways work. | D1. Work with ITC to identify menu of currently used predictive analytics, on-boarding, advising and monitoring technology tools. | D1. Provide recommendations that could be shared Technology Tools for Guided Pathways conference in March 2018 (by beginning of Winter 2018 quarter). | See above.
E. Identify meaningful strategies that support diversity, equity, and inclusion within the Guided Pathways Framework | E1. Partner with the WSSSC EDI Committee to embed EDI principles in Guided Pathway. | E1. Identify and build opportunities to broaden the understanding and application of EDI principles throughout the Guided Pathways. | The most explicit progress here has been an intentional and sustained framing of GP as a "tool" to adavnce equity. "Tool" is used loosely here as GP is a system redesign with a focus on intentionally removing barriers to success that our traditional approach(es) to HE applied, primarily to the determent of students of color and of poverty.
WSSSC / System Direction Goal: Equity, Diversity, and Inclusion ~ Embed and champion equity, diversity, and inclusion in and through the work of WSSSC and its Councils, and with its partners. Facilitated by Equity, Diversity, and Inclusion Committee
Objectives | Strategies | Intended Outcomes | Action/Updates
A. Embed Equity, Diversity and Inclusion (EDI) throughout the WSSSC and Council Work Plans | A1. Develop an aspirational statement or position statement about what EDI means to WSSSC. A2. Develop a framework (e.g., business case for diversity). 3A. Facilitate discussions with chief diversity officers and MSSDC to clarity scope and roles. A4. Complete needs assessment related to EDI knowledge-base, interests, etc. A5. Collaborate with the PD work group to leverage knowledge-base related to EDI. A6. Continue to partner with IC to embed EDI in the Pathways work. | A1. Express commitment and assure consistency of attention to and active, intentional ahearance to and action that advances that commitment. A2. Refine talking points and principles that will aid in the advancement of EDI throughout the CTC system. A3. Assist in building understanding and scope of responsibilities and opportunities across varied system structures with overlapping areas of engagement. A4. Acquire deeper understanding to inform priorities, strategies, and areas of impact. A5. Build opportunities (and take action) to integrate EDI principles into professional development. A6. Build opportunities for and organize inter-commission collaboration to broaden the understanding and application of EDI principles throughout the CTC system. | The EDI group have developed an aspirational statement that directly expresses our intent to advocate for equity and to identify and disrupt inequitable practices as we work toward serving the people in our respective communities. Additionally, the team drafted a business case for diversity that intentionally responds to WSSSC’s role in supporting SBCTC’s mission in consideration of both our present context and of the projected demographics shifts in Washington State. Together, these documents serve as our integrity statement and affirm our commitment to creating and sustaining systems characterized by equity, diversity, and inclusion.
System Direction Goal: Innovation ~ Use technology, collaboration and innovation to meet the demands of the economy, improve student success, and support guided pathways. Facilitated by Innovation & Technology Committee
Objectives | Strategies | Intended Outcomes | Action/Updates
A. Support & provide inputs through the established governance process for the ctcLink Project | A1. Actively participate in ctcLink project. A2. Identify opportunities to recognize, celebrate, and reward staff input, engagement, and accomplishments throughout project timeline. | A1. Lessons learned in FirstLink GoLive assist in a smoother transition for First Wave colleges. A2. Staff describe feeling recognized, consulted, and engaged in process. | Regular updates provide insight and opportunities to inform/influence implementation and considerations. Work around the admissions application has been a key part of the work this year.
B. Keep students on their selected educational pathway. | B1. Share best practices (both technology and systems related) for information sharing, degree mapping/audits, and advising. B2. Share best practices related to data use to support guided pathways efforts. | B1. Students complete educational goals on time. B2. CTC staff report access to data that informs their work with students. | See pathway discussion above, including technology strategies (heavy focus on data and communication tools).
C. Ensure equitable access to technology used within the ctc system. | C1. Provide support to colleges in meeting the requirements of state CIO policy 188. | C1. Colleges are in compliance with state CIO policy 188. | Professional development with regard to Policy 108 was provided during the winter. In addition, new technologies and their ability to be compliant and meet our standards has been a regular part of our conversations and strategies, both for the commission and the councils.
D. Reduce cost of technology and software for individual colleges. | D1. Advocate for state-wide contracts for technology and/or software that can reduce the cost for each individual college (e.g. Maxient; Everfi). D2. Survey CTCs on technology needs and seek consensus on tools that will best serve campus and student needs. | D1 & D2. Increased access to new technology for staff, faculty and students | Ongoing. These conversations are also a part of our Policy 108 compliance strategies in order to leverage opportunities of investment to drive improved compliance.
System Direction Goal: Student Success ~ Achieve increased educational attainment for all students across the state. Facilitated by Student Supports Committee
Objectives | Strategies | Intended Outcomes | Action/Updates
A. Increasing students’ academic achievement and attainment by removing barriers and improving campus learning environments and campus climate. | A1. Create a learning environment free of sexual harassment & assault for all learners A2. Decrease institutional FAFSA, WAFSA and financial aid process barriers for students. | A1a. Joint meeting with HR Commission on topics that overlap Title IX coordination and student conduct A1b. Document how campuses are using EverFi and develop best practices A2. Review the survey regarding the Data Sheet and identify best practices, including the minimum amount of data that is needed to be collected on the form | A1a. As we continue to explore the potential for "retiring" some of our councils, and as we see requests for new councils, one concept that has recently emerged is to develop a Title IX coord council, as the coordinators are split between student services and HR. This has prompted a potential next step to engage with HRMC. A1b. A systemwide survey was developed and garnered responses from about 20 colleges. The responses are being consolidated and will be presented at the next WSSSC meeting in May. Subsequent action steps will be determined following that review.
B. Research impact of new academic placement options. | B1. Continue to work in partnership with Instruction Commission, State Board, and Testing Centers for placement options. | B1a. Identify the impact and consequences of placement reciprocity in light of multiple measurements B1b. Address the social justice/equity/access issues raised by more expensive models | This work is largely being undertaken as a part of the Placement 360 workgroup. Liaisons to Istruction Commission, in particular, continue to provide updates with regard to the SmarterBalanced assessments and the challenges related to ongoing alterations to the exam and its administration.
WSSSC Goal: Professional Development ~ Strengthen and expand the knowledge, skill, and abilities of Student Services professionals within the system. Facilitated by Professional Development Committee
Objectives | Strategies | Intended Outcomes | Action/Updates
A. Present timely and relevant professional development sessions at commissions and council meetings with a focus on equity, diversity, and inclusion. | A1. Survey WSSSC and Councils on interest in professional development. Help identify speakers and facilitate trainings. A2. Embed Professional Development in WSSSC meeting as agenda items. A3. Approach Professional development through a student development outcome lens (CAS Standards, NASPA). A4. Continue to develop professional development opportunities that highlight and attend to overlapping and complimenting areas of student services and instruction in collaboration with the Instruction Commission. A5. Continue to integrate/embedd and advance the principles of EDI in all professional development activities through close communication with the EDI committee, as well as the CDEO group and MSSDC. | A1 & A2. Meaningful professional development at least twice per year at WSSSC and Council meetings. A3. Assure that WSSSC professional development activities align with the philosophies and principles of the field(s). A4 & A5. Countine the conversation about aligning student development outcomes with instructional outcomes under the umbrella of principles of equity, diversity, and inclusion. | A1: A survey is in development and will be distributed at the WSSSC spring meeting or shortly after. A2: Will be completed by utilizing survey results to drive agenda items, A3: Professional development at WSSSC meetings are slowly shifting from a "here is the information" to a more engaged discourse that moves us to deeper understanding and meaningful action to shape the work of the commission and our institutions. A4 & 5: In current planning for the annual joint summer meeting with IC, CDEOs, and potentially other partners.
B. Develop mentorship program for Chief Student Service Officers through WSSSC. | B1. Identify Mentors B2. Develop mentor expectations and plan | B1. Onboard new Chief Student Services officers to WSSSC B2. Create a safe and supportive network for new Chief Student Services officers to maximize system knowledge, skills, and abilities. | Process completed and approved by WSSSC. At-Large exec team member, Chio Flores, assigned to launch the program. Launch date TBD by Executive committee.