## Slide 1: ctcLink update & Focus on financial aid
Washington State Student Services Commission & Financial Aid Council Meeting
Dec. 3, 2020

## Slide 2: agenda
TOPIC | MINUTES | FACILITATOR
ctcLink Update – Project | 10 | Christy Campbell
ctcLink Update – Customer Support | 10 | Dani Bundy, Grant Rodeheaver
Financial Aid Concerns/Questions Highlights of response document | 20 | Christy Campbell, Dani Bundy
Communication Channels | 5 | Christy Campbell
ctcLink Governance & Enhancement Request Process | 5 | Christy Campbell
Questions | 10 | All

## Slide 3: Ctclink program status

## Slide 4: Replacement solutions
New Online Admissions Application will be ready for ctcLink colleges Jan. 28, 2021
CampusCE (Continuing Education) integration with ctcLink planned for completion in Feb 2021
  Eliminates double entry!

## Slide 5: OAA Timeline
Activity | Timeline | Status
Kastech SIT | Oct. 5 – 30, 2020 | Complete
ctcLink SIT | Nov. 11 – Dec. 18, 2020 | In progress
Kastech test scripts | Oct. 30, 2020 | Complete
Kastech training documents | Nov. 13, 2020 | Complete
ctcLink develop UAT test scripts | Nov. 11 – Dec. 18, 2020 | In progress
ctcLink develop training documents | Dec. 1 – Dec. 30, 2020 | In progress
College UAT/Training | Jan. 11 – 22, 2021 | Pending
DG2 & DG3 Go-Live | Jan. 28, 2021 | Pending

## Slide 6: OAA Go-Live Dates by Deployment Group
Deployment Group (DG) | Go-Live
DG2 & DG3 | Jan. 28, 2021
DG4 & DG5 DG4 OAA activities will align with DG5 implementation activities and timeline | October 2021
DG6 DG6 activities will align with DG6 implementation activities/timeline | March 2022
ctcLink Deployment Groups and High-Level Timeline

## Slide 7: CAMPUSCE Timeline
Activity | Timeline | Status
Report Writer Customization and UAT tested by colleges. CampusCE migrates to college production environments. | Sept 2020 | Complete, Sept 2020
CampusCE/ctcLink business process alignment prototype | Sept 2020 | Complete
Continuing Education Council (CEC) executive committee review processes and integration points for initial feedback | Oct/Nov 2020 | Complete
Unit Testing / System Integration Testing | Nov 2020 | In Process
CEC reviews processes and integration | Dec 2020 | Scheduled
User Acceptance Testing | Dec 2020–Jan 2021 | Pending
Deploy Integration / Go Live | Jan/Feb 2021 | Pending

## Slide 8: ctcLink Deployment Groups and Timeline

## Slide 9
Deployment Group 4 Timeline (High Level Phases) |  | Y
We are here

## Slide 10
Deployment Group 5 Timeline (High Level Phases) |  | G
We are here
Conversion Cycle 1 retired to better align with other deployment groups.
Estimated dates subject to change. Go-live date requires discussion with DG6 colleges and approval by ctcLink Steering Committee.

## Slide 11
Deployment Group 6 DRAFT Timeline (High-Level Phases) |  | G
Conversion Cycle 1 retired to better align with other deployment groups.
Estimated dates subject to change. Go-live date requires discussion with DG6 colleges and approval by ctcLink Steering Committee.
We are here

## Slide 12: Ctclink Customer Support

## Slide 13: CTCLINK SUPPORT update
ctcLink Customer Support (Dani)
  Staffing Update
  ctcLink Production Support Updates (handout/web)
Guided Pathways in ctcLink
  Sub-Plans (Dani)
  Meta-Majors (Grant)
ctcLink Accessibility Update (Grant)
  Update on Accessibility Testing by Level Access
  Update on Improvements
  ctcLink Accessibility web page

## Slide 14: Financial Aid in ctclink

## Slide 15: Today’s focus on financial aid in ctclink
FAC concerns provided by ctcLink Steering Committee WSSSC Representative
Concerns/Questions sorted by:
  Implementation phase (Pre-Go-Live)
  ctcLink Customer Support (Post-Go-Live)
Current Communication Channels/Protocol
ctcLink Project Governance
Notes: Christy

## Slide 16: The big picture
ctcLink is one global instance of PeopleSoft for all Washington community and technical colleges.
This means one global design (plus limited local configuration), which depends largely on consistent business processes across the college system.
Financial Aid is one of the few exceptions since each college/district interprets federal and state regulations independently and is responsible for local policies to adhere to regulations. This can cause confusion when transitioning to a common system.
Notes: Christy

## Slide 17: Implementation (Pre-Go-Live)
Improving Implementation Activities – Highlights
  Aid Year Rollover changes made based on lessons learned
    Note: Dependent on Oracle’s release of PeopleSoft Update Manager (PUM) 19
  Financial Aid documentation revamped in response to not having enough information
  More improvements are in the works
    Some issues identified are related to learning the system and not the system itself
    Some issues identified need local decisions
Notes: Dani

## Slide 18: customer support (Post go-live)
Post Go-Live Customer Support
  Increased capacity
  Beginning Dec. 11 – FA Webex sessions to support colleges with the awarding process
  Support during the Webex sessions will focus on understanding of ctcLink/PeopleSoft system (not local college policies and procedures). ctcLink system support
Satisfactory Academic Progress
  Testing a solution to eliminate basic education classes from SAP calculations
Notes: Dani

## Slide 19: Customer Support (Post Go-live), Cont.
Support Materials
  Revising some materials to incorporate the explanation of the different steps to process aid.
Queries
  Existing queries have been developed by SBCTC Data Services and some Colleges
  Successful query requires understanding college data to confirm it returns the desired results
  Question tickets to Data Services for support
Notes: Dani

## Slide 20: Ctclink Communication channels

## Slide 21: Ctclink Communication channels – pre Go-live ctclink project
Thursday UAT check-in sessions (during UAT)
Weekly Project Manager Meetings
Monthly Executive Sponsor Meetings (project member attends for Org. Change Mgmt. support)
Monthly All College Project Manager Meetings
ctcLink Project-College Communication - Who should pre-go-live colleges talk to about ctcLink?
Notes: Christy

## Slide 22: Ctclink Communication channels – post go-live ctclink support
Weekly Customer Support Workshops (by pillar/module)
Weekly Project Management Meetings (live colleges)
Developing System Technology Groups (FAST)
Listservs (eLists)
Notes: Dani

## Slide 23: customer support lists for live colleges
Customer Support sends updates, outage notices, changes to configuration, training, workshops, and more.
Ask your peers how-to questions and best practices.
Click to join a list!
  ctcLinkSME-HCM – Human Capital Management
  ctcLinkSME_FIN - Finance
  ctcLinkSME_StuFin – Student Financials
  ctcLinkFinAidSupport – Financial Aid
  ctcLinkCSSupport – Campus Solutions
  ctcLinkSME-rpt – General Reporting
  ctcLink-coding – General Coding
  ctcLink-Security – Security
Lists not intended for Service Desk, support or questions about system issues. Submit tickets to the ServiceDesk following the Tier Support plan.
Notes: Who may join?
At this time, we strongly encourage anyone live on ctcLink PeopleSoft — including ctcLink Project Team and SBCTC staff members to join — especially those using FIN, HCM, CS, coding and reporting staff.
Only Washington state community and technical college system .edu domain addresses will be approved for subscription.

## Slide 24: Ctclink governance and enhancement Request process

## Slide 25: ctcLink governance framework

## Slide 26: ctcLink Work Priorities & Governance Policy
The ctcLink Change Management and Prioritization policy outlines how changes to ctcLink PeopleSoft in production (live on ctcLink) are received and prioritized by SBCTC IT and ctcLink Support.
How are approved changes to ctcLink prioritized for implementation?
Who may submit Enhancement Requests to the ctcLink Working Group?
How do individual users, commissions, councils and other stakeholders with ideas/requests for changes and enhancements partner with ctcLink governance (i.e. ctcLink Working Group), ctcLink Project and SBCTC IT ctcLink Support?

## Slide 27: Questions?